## README
UniConnect — Student Portal Consolidation — Project data workbook
BISY2004 Assessment 2 ¦ Group XX ¦ Scenario C ¦ Fictional organisation: Southern Coast University (SCU) — fictional ¦ Status date: Fri 25 Sep 2026 ¦ Maintained by: Sabikunnhar
Everything comes from one data file (data/project.yaml), so the WBS IDs are the same in ProjectLibre, Trello, this workbook and the diagrams. Numbers you type in are inputs; everything else is a formula.
Sheet | Purpose | Maintained by
Resources | Role rates (AUD/hour) and headcount — input to all labour costs | Aman Maharjan
Assignments | Task × role × units → hours × rate = labour cost (formulas) | Aman Maharjan
Schedule_WBS | WBS work packages with ProjectLibre IDs, baseline/forecast dates, float, cost, % complete, PV/EV/AC | Aman Maharjan
Risk_Register | 13 risks, 5×5 scoring (Score = L×I), rating bands, residual risk, EMV → contingency reserve | Mohammed Talha Razi
Risk_Heatmap_5x5 | Inherent and residual heat maps (COUNTIFS) with risk IDs in each cell | Mohammed Talha Razi
Cost_Baseline | Cost by WBS branch, BAC, contingency + management reserve, total budget, monthly time-phased PV | Aman Maharjan
EVM_Status | Weekly PV/EV/AC to the status date; SV, CV, SPI, CPI, EAC (3 methods), ETC, VAC, TCPI with RAG | Aman Maharjan
Dashboard | KPI tiles, S-curve, risks by rating, milestone status, quality status | Aman Maharjan
Stakeholder_Register | Power/interest scores, quadrant formula, reason, attitude current→desired, strategy | Sabikunnhar
Comms_Plan | Who gets what, how, how often, owner, feedback loop | Mohammed Talha Razi
RACI | Deliverables × roles with an 'exactly one A' check per row | Mohammed Talha Razi
Quality_Metrics | Metrics, targets, current values, RAG | Mohammed Talha Razi
Control_Chart | Defects per week with mean, UCL = mean + 3σ, LCL = max(0, mean − 3σ) | Mohammed Talha Razi
Change_Log | CR-01..03 with scope/schedule/cost/risk impact and CCB decision | Mohammed Talha Razi
Issue_Log | ISS-01..05 linked to risks, WBS, owners and actions | Aman Maharjan
Traceability | WBS → ProjectLibre ID → Trello card → cost → risks → RACI accountable → quality metric | Sabikunnhar
Closure | Closure checklist, benefits realisation plan, lessons learned | Aman Maharjan
Lookups | Validation lists and the 5×5 scoring scales | Sabikunnhar
Status colours
Green | on target (SPI/CPI 0.95 or more)
Amber | keep an eye on it (0.90 to 0.95)
Red | needs action now (under 0.90)
Grey | not measured yet
Note | Colour is only used for status. The word is always in the cell as well.
Our group
Sabikunnhar (group leader) | Group leader. Project charter, scope and WBS, stakeholders, integration and the final recommendation. Built and runs the website and puts the evidence pack together.
Aman Maharjan | Schedule and cost. Built the ProjectLibre schedule (baseline, critical path, progress) and looks after cost, EVM, the dashboard, the issue log and closure.
Mohammed Talha Razi | Risk, quality, change and team. Risk register and heat map, quality metrics and control chart, change log and change-control flow, the Trello board, team structure, RACI and comms plan.

## Dashboard
UniConnect — Project status dashboard (status date 25 Sep 2026)
Every tile is a formula that pulls from EVM_Status, Risk_Register, Issue_Log, Change_Log and Quality_Metrics. ¦ Maintained by: Aman Maharjan
SPI |  |  |  | CPI |  |  | % complete |  | EAC
0.91363 |  |  |  | 0.95728 |  |  | 24.64% |  | 940353.926
VAC |  |  |  | Open High risks |  |  | Open issues |  | CRs approved
-40173.926 |  |  |  | 7 |  |  | 3 |  | 2 of 3
Overall RAG | AMBER |  | Forecast go-live 04/02/2027 vs hard deadline 05/02/2027 — buffer 1 working day(s) before CR-02 recovery
Milestones | [6 empty] | Quality metrics
ID | Milestone |  | Baseline | Forecast | Slip (d) | Status | ID | Metric | Current | RAG
M1 | Charter approved |  | 2026-07-17 | 2026-07-17 | 0 | Achieved | Q01 | Migration record accuracy | 95.3% (trial 1) | Red
M2 | Design sign-off |  | 2026-09-04 | 2026-09-04 | 0 | Achieved | Q02 | Portal availability | 99.2% (test env.) | Amber
M3 | Build complete |  | 2026-10-26 | 2026-10-26 | 0 | On track | Q03 | Page load p95 at 5,000 concurrent users | Not yet tested | Grey
M4 | Trial migration passed |  | 2026-11-02 | 2026-11-16 | 10 | At risk | Q04 | WCAG 2.1 AA critical failures | 2 (Sprint 1 scan) | Amber
M5 | UAT sign-off |  | 2026-12-14 | 2027-01-06 | 10 | At risk | Q05 | UAT pass rate | Not started | Grey
M6 | Go-live |  | 2027-01-20 | 2027-02-04 | 10 | At risk | Q06 | Open Severity-1 defects at go-live | 1 open (ISS-02) | Amber
M7 | Project closed |  | 2027-03-11 | 2027-03-25 | 10 | At risk | Q07 | Portal-related helpdesk tickets | Baseline 4,200/month | Grey
Risks by rating
Rating | Inherent | Residual
Extreme | 0 | 0
High | 7 | 1
Medium | 6 | 7
Low | 0 | 5
Formulas:
Slip (d) = IF([CPI]<=[Baseline],0,NETWORKDAYS([Baseline],[CPI],Holidays)-1)

## Risk_Register
Risk register (5×5)
Score = L × I; bands Low 1–4, Medium 5–9, High 10–16, Extreme 20–25; EMV = probability × cost impact ¦ Maintained by: Mohammed Talha Razi
ID | Type | Category | Description (cause → event → effect) | WBS links | L | I | Score | Rating | Owner | Strategy | Response | Trigger | Res. L | Res. I | Res. score | Res. rating | Probability | Cost impact | EMV | Status | Heat key | Res. key
R01 | threat | Data | Because legacy SIS/portal data has duplicate and inconsistent student records (cause), trial migration may fail reconciliation (event), delaying the critical migration path and go-live (effect). | 4.1, 4.2, 4.3 | 4 | 4 | 16 | High | Data Engineer | Mitigate | Early data profiling in 2.1; de-duplication rules in 4.1; reconciliation scripts; contingency: cleansing mini-sprint + contractor. | > 1% duplicate/unmatched records in trial migration 1 | 2 | 3 | 6 | Medium | 65% | 60000 | 39000 | Materialised → ISS-01 | 4-4 | 2-3
R02 | threat | Technical/Vendor | Because the LMS vendor's SSO/API support is immature (cause), SSO or LMS integration may not work (event), delaying Sprint 1 and integration APIs (effect). | 2.3, 3.1, 3.5 | 3 | 4 | 12 | High | Solution Architect | Mitigate | SSO proof of concept in Sprint 1; vendor SLA with escalation; weekly vendor call (C07). | SSO PoC fails token exchange by end of Sprint 1 | 2 | 3 | 6 | Medium | 40% | 15000 | 6000 | Open — partly occurred (ISS-02) | 3-4 | 2-3
R03 | threat | Compliance/Privacy | Because migration copies identifiable student data between environments (cause), personal information could be exposed (event), causing a notifiable data breach under APP 11 (effect). | 2.4, 4.2, 4.3, 4.4 | 2 | 5 | 10 | High | Privacy Officer | Mitigate | PIA; masked data in non-production; encrypted transfer; access logging; MFA for all users (CR-03). | Any unmasked personal data found in a non-production environment | 1 | 5 | 5 | Medium | 15% | 40000 | 6000 | Open | 2-5 | 1-5
R04 | threat | Schedule | Because go-live is close to Semester 1 enrolment (cause), cutover could clash with the enrolment peak (event), disrupting enrolments (effect). | 4.4, 6.3 | 3 | 4 | 12 | High | Project Manager | Avoid | Fixed cutover window 14–20 Jan 2027, change freeze from 1 Feb; fallback: go-live in mid-semester break with legacy portals kept live. | Forecast go-live later than 29 Jan 2027 | 1 | 4 | 4 | Low | 40% | 15000 | 6000 | Open — watch (forecast go-live 4 Feb vs 5 Feb deadline) | 3-4 | 1-4
R05 | threat | Resource | Because developers are in high demand (cause), a key developer may resign (event), slowing sprints (effect). | 3.1, 3.2, 3.3, 3.4 | 2 | 3 | 6 | Medium | Development Lead | Mitigate | Pair programming, documented code, retention bonus at go-live. | Resignation notice from a developer | 2 | 2 | 4 | Low | 15% | 15000 | 2250 | Open | 2-3 | 2-2
R06 | threat | Scope | Because faculties want their own features (cause), unapproved scope may enter sprints (event), consuming float and budget (effect). | 2.2, 3.2, 3.3, 3.4 | 4 | 3 | 12 | High | Project Manager | Mitigate | MoSCoW backlog; all requests through CCB (C05); Phase 2 backlog. | > 2 new feature requests in a sprint | 2 | 3 | 6 | Medium | 65% | 10000 | 6500 | Occurred → CR-01 deferred | 4-3 | 2-3
R07 | threat | Technical/Performance | Because 5,000+ students log in at once during enrolment (cause), the portal could slow or fail (event), stopping enrolments (effect). | 5.4, 6.3 | 3 | 5 | 15 | High | Solution Architect | Mitigate | Load test at 5,000 concurrent users; autoscaling; CDN caching. | p95 page load > 2 s in load test | 2 | 4 | 8 | Medium | 40% | 15000 | 6000 | Open | 3-5 | 2-4
R08 | threat | Compliance/Accessibility | Because legacy templates are not accessible (cause), the portal may fail WCAG 2.1 AA (event), excluding students with disability (effect). | 2.5, 5.3 | 3 | 3 | 9 | Medium | UX Designer | Mitigate | Accessible design system; automated scans each sprint; audit 5.3. | Any critical failure in a sprint accessibility scan | 1 | 3 | 3 | Low | 40% | 10000 | 4000 | Open — ISS-04 | 3-3 | 1-3
R09 | threat | Organisational | Because students are used to the old portals (cause), adoption may be low (event), reducing benefits (effect). | 6.1, 6.2 | 3 | 3 | 9 | Medium | Change & Training Lead | Mitigate | SRC co-design; pilot champions; go-live campaign (C04, C08). | Pilot satisfaction < 70% | 2 | 2 | 4 | Low | 40% | 8000 | 3200 | Open | 3-3 | 2-2
R10 | threat | Financial | Because licences are priced in USD (cause), a weaker AUD could raise licence costs (event), exceeding the cost baseline (effect). | 6.3 | 3 | 3 | 9 | Medium | Finance Office | Transfer | Fixed-AUD pricing clause negotiated with the vendor. | AUD/USD < 0.62 before contract signature | 1 | 3 | 3 | Low | 40% | 10000 | 4000 | Open — fixed-AUD clause in negotiation | 3-3 | 1-3
R11 | threat | Operational | Because all students switch at once (cause), the Service Desk may be overwhelmed (event), causing long waits and complaints (effect). | 6.1, 6.4 | 4 | 3 | 12 | High | Change & Training Lead | Mitigate | FAQs, chatbot, surge staff roster, daily hypercare stand-up (C09). | > 300 portal tickets/day during hypercare | 2 | 3 | 6 | Medium | 65% | 8000 | 5200 | Open | 4-3 | 2-3
R12 | opportunity | Opportunity | Because SCU already runs an identity platform (cause), SSO could reuse it (event), avoiding a separate identity licence and speeding Sprint 1 (effect). | 2.3, 3.1 | 3 | 3 | 9 | Medium | Solution Architect | Exploit | Design SSO on the existing platform; cancel separate IdP quote. | Architecture review confirms compatibility | 5 | 3 | 15 | High | 40% | -30000 | -12000 | Realised in 2.3 (saving not netted from reserve) | 3-3 | 5-3
R13 | threat | Schedule | Because of the university shutdown and staff leave over summer (cause), key people may be unavailable (event), slowing the faculty pilot (effect). | 6.2 | 4 | 2 | 8 | Medium | Project Manager | Accept | Accepted: shutdown modelled in the ProjectLibre calendar; leave plan agreed by Oct. | Leave requests overlapping 6.2 | 4 | 2 | 8 | Medium | 65% | 4000 | 2600 | Accepted | 4-2 | 4-2
[12 empty] | Contingency reserve (threat EMV) | [6 empty] | 90750
[12 empty] | Opportunity EMV (not netted) | [6 empty] | -12000
[12 empty] | High/Extreme risks open | [6 empty] | 7

## Risk_Heatmap_5x5
5×5 risk heat map (inherent and residual)
Each cell counts the risks at that likelihood and impact (COUNTIFS), then shows the band and the risk IDs. Bands (the cell colour shows them too): 1–4 Low (green), 5–9 Medium (yellow), 10–16 High (orange), 20–25 Extreme (red). ¦ Maintained by: Mohammed Talha Razi
Inherent risk (before response) | [5 empty] | Residual risk (after response)
Likelihood ↓ / Impact → | 1 Insignificant | 2 Minor | 3 Moderate | 4 Major | 5 Severe | Likelihood ↓ / Impact → | 1 Insignificant | 2 Minor | 3 Moderate | 4 Major | 5 Severe
5 Almost certain | [5 empty] | 5 Almost certain |  |  | 1 · High R12
4 Likely |  | 1 · Medium R13 | 2 · High R06 R11 | 1 · High R01 |  | 4 Likely |  | 1 · Medium R13
3 Possible |  |  | 4 · Medium R08 R09 R10 R12 | 2 · High R02 R04 | 1 · High R07 | 3 Possible
2 Unlikely |  |  | 1 · Medium R05 |  | 1 · High R03 | 2 Unlikely |  | 2 · Low R05 R09 | 4 · Medium R01 R02 R06 R11 | 1 · Medium R07
1 Rare | [5 empty] | 1 Rare |  |  | 2 · Low R08 R10 | 1 · Low R04 | 1 · Medium R03
Risks plotted | 13 |  |  |  |  | Risks plotted | 13
Counts match? | OK
What it shows: seven threats start as High (R01 at 4×4 is the worst one). After our responses none of them is above Medium. R03 stays Medium (1×5) because a data breach would still be really bad. R12 is an opportunity, so we want it to happen: its residual score (5×3) being high is a good thing.

## Cost_Baseline
Cost baseline, reserves and budget (AUD)
UniConnect — Student Portal Consolidation ¦ Status date 25/09/2026 ¦ Source: data/project.yaml ¦ Maintained by: Aman Maharjan
WBS | Level-1 deliverable | Labour hours | Labour cost | Fixed / material | Subtotal | % of BAC | Month | Planned value (month) | Cumulative PV | % of BAC
1 | Project Management | 1120 | 125520 | 0 | 125520 | 13.94% | Jul 2026 | 42500 | 42500 | 4.721%
2 | Requirements & Design | 700 | 76900 | 0 | 76900 | 8.543% | Aug 2026 | 72960 | 115460 | 12.83%
3 | Portal Build (Agile) | 1500 | 150800 | 0 | 150800 | 16.75% | Sep 2026 | 143480 | 258940 | 28.77%
4 | Data Migration | 740 | 76400 | 0 | 76400 | 8.487% | Oct 2026 | 136190 | 395130 | 43.89%
5 | Testing & Quality | 1140 | 115160 | 25000 | 140160 | 15.57% | Nov 2026 | 113120 | 508250 | 56.46%
6 | Deployment & Transition | 1040 | 106400 | 224000 | 330400 | 36.7% | Dec 2026 | 56610 | 564860 | 62.75%
[7 empty] | Jan 2027 | 275250 | 840110 | 93.33%
| Cost baseline (BAC) | 6240 | 651180 | 249000 | 900180 | 100% | Feb 2027 | 49370 | 889480 | 98.81%
| Contingency reserve (Σ threat EMV, Risk_Register) |  |  |  | 90750 | 10.08% | Mar 2027 | 10700 | 900180 | 100%
| Performance measurement baseline = BAC + contingency |  |  |  | 990930 |  | Monthly PV is time-phased from the ProjectLibre baseline (flat work contour).
| Management reserve (5% of BAC, sponsor-held) |  |  |  | 45009 | 5%
| Total project budget |  |  |  | 1035939
| Check: BAC equals Schedule_WBS total |  |  |  | OK

## EVM_Status
Earned value status (to 25 Sep 2026)
Weekly cumulative PV/EV/AC from the ProjectLibre baseline and progress; summary uses the Schedule_WBS task totals ¦ Maintained by: Aman Maharjan
Status-date summary
Week | Week ending | PV (cum) | EV (cum) | AC (cum) | SV | CV | SPI | CPI | Budget at completion (BAC) | 900180 |  | Cost baseline (Schedule_WBS)
1 | 2026-07-10 | 6700 | 6700 | 6700 | 0 | 0 | 1 | 1 | Planned value (PV / BCWS) | 242800 |  | ProjectLibre BCWS at status date
2 | 2026-07-17 | 13400 | 13400 | 13400 | 0 | 0 | 1 | 1 | Earned value (EV / BCWP) | 221830 |  | % complete × baseline cost
3 | 2026-07-24 | 28900 | 28900 | 28900 | 0 | 0 | 1 | 1 | Actual cost (AC / ACWP) | 231730 |  | ProjectLibre actual cost
4 | 2026-07-31 | 42500 | 42500 | 42500 | 0 | 0 | 1 | 1 | Schedule variance SV = EV − PV | -20970 |  | Negative = behind schedule
5 | 2026-08-07 | 53650 | 53650 | 53650 | 0 | 0 | 1 | 1 | Cost variance CV = EV − AC | -9900 |  | Negative = over budget
6 | 2026-08-14 | 64800 | 64800 | 64800 | 0 | 0 | 1 | 1 | SPI = EV / PV | 0.91363 | Amber | < 1 behind schedule
7 | 2026-08-21 | 83350 | 83350 | 85210 | 0 | -1860 | 1 | 0.97817 | CPI = EV / AC | 0.95728 | Green | < 1 over budget
8 | 2026-08-28 | 107000 | 107000 | 110720 | 0 | -3720 | 1 | 0.9664 | EAC (typical) = BAC / CPI | 940353.926 |  | Current cost efficiency continues
9 | 2026-09-04 | 149300 | 147200 | 152180 | -2100 | -4980 | 0.98593 | 0.96728 | EAC (atypical) = AC + (BAC − EV) | 910080 |  | Variance treated as one-off
10 | 2026-09-11 | 180600 | 176400 | 182640 | -4200 | -6240 | 0.97674 | 0.96583 | EAC (CPI × SPI) = AC + (BAC − EV)/(CPI×SPI) | 1007341.4557 |  | Schedule pressure also drives cost
11 | 2026-09-18 | 211700 | 199115 | 207185 | -12585 | -8070 | 0.94055 | 0.96105 | ETC = EAC − AC | 708623.926 |  | Cost to finish (typical)
12 | 2026-09-25 | 242800 | 221830 | 231730 | -20970 | -9900 | 0.91363 | 0.95728 | VAC = BAC − EAC | -40173.926 |  | Forecast overrun (typical)
13 | 2026-10-02 | 269700 | [6 empty] | TCPI = (BAC − EV)/(BAC − AC) | 1.0148 |  | > 1 = must work more efficiently
14 | 2026-10-09 | 293660 | [6 empty] | % complete (EV / BAC) | 24.64% |  | Physical progress
15 | 2026-10-16 | 321370 | [6 empty] | % planned (PV / BAC) | 26.97% |  | Where we should be
16 | 2026-10-23 | 352920 | [6 empty] | Contingency reserve | 90750 |  | Covers VAC?
17 | 2026-10-30 | 395130 | [6 empty] | EAC within BAC + contingency? | Yes |  | Funding test for the recommendation
18 | 2026-11-06 | 437130
19 | 2026-11-13 | 465600
20 | 2026-11-20 | 490850 | [6 empty] | RAG thresholds: ≥ 0.95 Green · 0.90–0.95 Amber · < 0.90 Red (agreed with sponsor).
21 | 2026-11-27 | 505780 | [6 empty] | Weekly row matches task totals? | OK
22 | 2026-12-04 | 526210
23 | 2026-12-11 | 546640
24 | 2026-12-18 | 558110
25 | 2026-12-25 | 564860
26 | 2027-01-01 | 564860
27 | 2027-01-08 | 576510
28 | 2027-01-15 | 679040
29 | 2027-01-22 | 827910
30 | 2027-01-29 | 840110
31 | 2027-02-05 | 855360
32 | 2027-02-12 | 870610
33 | 2027-02-19 | 884480
34 | 2027-02-26 | 889480
35 | 2027-03-05 | 894820
36 | 2027-03-12 | 900180

## Stakeholder_Register
Stakeholder register & power–interest classification
Quadrant formula: power ≥ 4 and interest ≥ 4 → Manage closely; power ≥ 4 → Keep satisfied; interest ≥ 4 → Keep informed; else Monitor ¦ Maintained by: Sabikunnhar
ID | Stakeholder | Role | Power (1–5) | Interest (1–5) | Quadrant (formula) | Reason for classification | Current attitude | Desired attitude | Engagement strategy | Comms ref
S01 | Deputy Vice-Chancellor (Education) | Project sponsor | 5 | 5 | Manage closely | Funds the project, chairs the steering committee and owns the go/no-go decision. | Supportive | Leading | Fortnightly steering committee; early warning of variances; decisions requested with options. | C01, C05
S02 | Chief Information Officer | IT executive | 5 | 4 | Manage closely | Owns IT architecture, operations and the identity platform; can reprioritise IT staff. | Supportive | Leading | Steering committee member; architecture decisions escalated directly. | C01, C02
S03 | Academic Registrar | Data owner — student records | 4 | 5 | Manage closely | Owns enrolment and student data; signs migration reconciliation; worried about enrolment disruption. | Neutral | Supportive | Involve in cleansing decisions and reconciliation sign-off; privacy briefings before each migration. | C01, C06
S04 | Faculty Deans | Academic leadership | 4 | 3 | Keep satisfied | Can escalate to the DVC and control faculty staff time, but day-to-day interest is moderate. | Resistant | Neutral | Monthly faculty briefings; route feature requests through the CCB (CR-01). | C11, C02
S05 | Students (domestic & international) | Primary users | 2 | 5 | Keep informed | Most affected by the change but have no formal decision rights; influence is via the SRC. | Unaware | Supportive | Co-design via SRC, pilot, newsletters and go-live campaign; multilingual guides for international students. | C04, C08
S06 | Student Representative Council (SRC) | Student voice | 3 | 4 | Keep informed | Speaks for students and can create reputational pressure, but has no budget or approval authority. | Neutral | Supportive | Sprint review participation; co-design sessions; pilot champions. | C03, C04
S07 | Academic staff | Secondary users (LMS gateway) | 2 | 3 | Monitor | Affected only via LMS links and student questions; little authority over the project. | Unaware | Neutral | General updates through faculty briefings; quick-reference guide. | C11
S08 | IT Service Desk | Support provider | 2 | 4 | Keep informed | Absorbs go-live ticket volume (R11) but does not approve scope or budget. | Concerned | Supportive | Early training, knowledge base, hypercare stand-ups. | C08, C09
S09 | Finance Office | Budget & fees integration | 4 | 3 | Keep satisfied | Releases funds and owns the fees system, but is interested mainly in cost and integration points. | Neutral | Supportive | Monthly cost/EVM summary; CCB member for cost-affecting changes. | C01, C05
S10 | Privacy Officer | Compliance (Privacy Act/APPs) | 4 | 4 | Manage closely | Can halt migration on privacy grounds and must approve the PIA (R03, CR-03). | Cautious | Supportive | PIA co-owner; privacy briefing before every migration; CCB member. | C06, C05
S11 | Accessibility Services | Disability advocacy | 2 | 4 | Keep informed | Advocates for students with disability (WCAG, R08) but has advisory, not approval, power. | Neutral | Supportive | Prototype testing and WCAG audit review; sprint reviews. | C03
S12 | LMS vendor | Supplier — LMS API | 4 | 2 | Keep satisfied | Controls the LMS API and SSO support (R02) through the contract, but has low interest in our timeline. | Neutral | Supportive | Weekly vendor call; SLA escalation path via the CIO. | C07
S13 | Portal platform vendor | Supplier — portal platform | 3 | 4 | Keep informed | Keen on a reference site; limited leverage because the contract is signed. | Supportive | Supportive | Weekly vendor call; joint defect triage. | C07
S14 | TEQSA (regulator) | External regulator | 5 | 1 | Keep satisfied | Can impose conditions on the university but is only interested if student outcomes or data are compromised. | Unaware | Neutral | Keep satisfied via the Registrar's routine compliance reporting; notify only if a material incident occurs. | C10
| Manage closely | 4
| Keep satisfied | 4
| Keep informed | 5
| Monitor | 1

## Comms_Plan
Communication plan
UniConnect — Student Portal Consolidation ¦ Status date 25/09/2026 ¦ Source: data/project.yaml ¦ Maintained by: Mohammed Talha Razi
ID | Audience | Information | Method | Frequency | Owner | Feedback | Stakeholders served
C01 | Steering committee (DVC, CIO, Registrar, Finance) | Status dashboard, EVM, top risks, decisions needed | Meeting + dashboard PDF | Fortnightly | Project Manager | Minutes and action log | S01, S02, S03, S09
C02 | Sponsor, CIO, Deans, Privacy Officer | Weekly status report (RAG, SPI/CPI, issues) | Email report | Weekly (Friday) | Project Manager | Reply/queries to PM | S02, S04
C03 | Registrar's team, SRC, Accessibility Services | Sprint demo of working features | Sprint review (hybrid meeting) | Every 2 weeks | Development Lead | Backlog items raised in Trello | S06, S11
C04 | Students | What is changing, when, pilot invitations | Newsletter, portal banner, social media | Monthly; weekly from Dec | Change & Training Lead | Survey and SRC channel | S05, S06
C05 | Change Control Board | Change requests with impact analysis | CCB meeting | Fortnightly or ad hoc | Project Manager | Decision recorded in change log | S01, S09, S10
C06 | Privacy Officer, Registrar | Migration controls, masking, reconciliation results | Privacy briefing | Before each migration run | Data Engineer | Written approval to proceed | S03, S10
C07 | LMS vendor, portal platform vendor | Integration defects, API changes, SLAs | Vendor call | Weekly | Solution Architect | Joint defect log | S12, S13
C08 | Students, staff, IT Service Desk | Go-live comms pack: how to log in, where to get help | Email, intranet, FAQs, posters | 4 weeks, 1 week and day 0 before go-live | Change & Training Lead | Help-page analytics, tickets | S05, S08
C09 | IT Service Desk, Dev, Data Engineer | Incidents, ticket trends, fixes | Stand-up (15 min) | Daily during hypercare | Project Manager | Incident log | S08
C10 | TEQSA (via Registrar) | Compliance summary; material incidents only | Formal report | Quarterly / as required | Academic Registrar | Regulator correspondence | S14
C11 | Faculty Deans, academic staff | Scope, dates, pilot, LMS link changes | Faculty briefing | Monthly | Project Manager | Q&A; requests routed to CCB | S04, S07

## RACI
RACI matrix
Exactly one A (Accountable) per deliverable — checked by formula ¦ Maintained by: Mohammed Talha Razi
Deliverable | WBS | Sponsor | Project Manager | Business Analyst | Solution Architect | Development Lead | Data Engineer | Test Lead | UX Designer | Change & Training Lead | Privacy Officer | A count | Check
Project charter | 1.1 | A | R | C | I | I | I | I | I | I | C | 1 | OK
PM plan & baselines / monitoring & control | 1.2, 1.3 | I | A | R | C | C | C | C | I | C | I | 1 | OK
Requirements & audit | 2.1, 2.2 | I | C | A | C | C | R | I | R | C | C | 1 | OK
Solution & SSO architecture | 2.3 | I | C | C | A | R | C | I | C | I | C | 1 | OK
Privacy Impact Assessment | 2.4 | I | C | R | C | I | C | I | I | I | A | 1 | OK
UX prototype & accessibility | 2.5, 5.3 | I | I | C | I | C | I | R | A | C | I | 1 | OK
Portal features (Sprints 1–4) & configuration | 3.1, 3.2, 3.3, 3.4, 3.6 | I | C | R | C | A | I | R | R | I | I | 1 | OK
Integration APIs & load testing | 3.5, 5.4 | I | I | C | A | R | C | R | I | I | I | 1 | OK
Data migration (mapping, trials, final) | 4.1, 4.2, 4.3, 4.4 | I | C | R | C | C | A | R | I | I | C | 1 | OK
Testing (SIT, security, UAT, regression) | 5.1, 5.2, 5.5, 5.6 | I | C | R | C | R | C | A | C | C | C | 1 | OK
Training, pilot & go-live cutover | 6.1, 6.2, 6.3 | C | A | C | R | R | R | C | I | R | I | 1 | OK
Hypercare, decommissioning & closure | 6.4, 6.5, 1.4 | C | A | R | R | R | R | C | I | R | C | 1 | OK
R = Responsible · A = Accountable (one per row) · C = Consulted · I = Informed

## Quality_Metrics
Quality metrics
UniConnect — Student Portal Consolidation ¦ Status date 25/09/2026 ¦ Source: data/project.yaml ¦ Maintained by: Mohammed Talha Razi
ID | Metric | Target | Measurement method | Frequency | Owner | Current value | RAG | WBS
Q01 | Migration record accuracy | ≥ 99.5% reconciled | Automated reconciliation report vs source counts | Each trial run | Data Engineer | 95.3% (trial 1) | Red | 4.3
Q02 | Portal availability | ≥ 99.5% | Uptime monitoring | Monthly | Solution Architect | 99.2% (test env.) | Amber | 6.4
Q03 | Page load p95 at 5,000 concurrent users | < 2 s | Load test tool (5.4) | Load test + go-live | Solution Architect | Not yet tested | Grey | 5.4
Q04 | WCAG 2.1 AA critical failures | 0 | Automated scan each sprint + audit | Each sprint | UX Designer | 2 (Sprint 1 scan) | Amber | 5.3
Q05 | UAT pass rate | ≥ 95% | UAT scripts passed / executed | Daily in UAT | Test Lead | Not started | Grey | 5.5
Q06 | Open Severity-1 defects at go-live | 0 | Defect tracker | Weekly | Test Lead | 1 open (ISS-02) | Amber | 5.6
Q07 | Portal-related helpdesk tickets | −30% within 3 months | Service Desk reports vs 4,200/month baseline | Monthly after go-live | Change & Training Lead | Baseline 4,200/month | Grey | 6.4

## Control_Chart
Control chart — defects logged per week
Mean and σ from the stable baseline period (weeks 3–11); UCL = mean + 3σ; LCL = max(0, mean − 3σ) ¦ Maintained by: Mohammed Talha Razi
Week | Week ending | Defects | Mean | UCL | LCL | Out of control? | Baseline mean | 6
3 | 2026-07-24 | 6 | 6 | 9.6742 | 2.3258 | No | Baseline σ (sample) | 1.2247
4 | 2026-07-31 | 5 | 6 | 9.6742 | 2.3258 | No | UCL | 9.6742
5 | 2026-08-07 | 7 | 6 | 9.6742 | 2.3258 | No | LCL | 2.3258
6 | 2026-08-14 | 4 | 6 | 9.6742 | 2.3258 | No
7 | 2026-08-21 | 6 | 6 | 9.6742 | 2.3258 | No
8 | 2026-08-28 | 5 | 6 | 9.6742 | 2.3258 | No
9 | 2026-09-04 | 8 | 6 | 9.6742 | 2.3258 | No
10 | 2026-09-11 | 6 | 6 | 9.6742 | 2.3258 | No
11 | 2026-09-18 | 7 | 6 | 9.6742 | 2.3258 | No
12 | 2026-09-25 | 14 | 6 | 9.6742 | 2.3258 | YES — investigate
Interpretation: Week 12 (14 defects) is above the UCL: a special cause, traced to duplicate records in trial migration 1 (ISS-01), not random variation. Action: root-cause analysis and CR-02.

## Change_Log
Change log (CCB decisions)
UniConnect — Student Portal Consolidation ¦ Status date 25/09/2026 ¦ Source: data/project.yaml ¦ Maintained by: Mohammed Talha Razi
CR | Date | Requester | Description | WBS affected | Risks / issues | Scope impact | Schedule impact | Cost impact | Risk impact | CCB decision | CCB date | Rationale | Baseline updated | Artefacts updated
CR-01 | 2026-08-26 | Faculty of Business (Dean) | Add mobile push notifications for timetable and fee reminders. | 3.2, 3.6 | R06, ISS-03 | New feature + native app work (out of scope) | +10 working days on Sprint 2/3 (critical-path pressure) | +$42,000 | Raises R06 and R05 | Deferred | 2026-09-02 | Scope creep; would consume float and threaten go-live. Added to Phase 2 backlog. Email notifications (3.6) cover the need. | No | Change log, Phase 2 backlog (Trello), comms to Deans (C11)
CR-02 | 2026-09-24 | Data Engineer / Project Manager | Add a data-cleansing mini-sprint and a 3-week contract data engineer to recover trial migration 1 (response to ISS-01). | 4.2, 4.3 | R01, R04, ISS-01 | No change to product scope; adds cleansing activity | Recovers about 8 of the 10 forecast slip days (crashing 4.2/4.3 + fast-tracking SIT preparation) | +$23,800 (contractor $15,600 + internal effort $8,200) from contingency reserve | Reduces R01 and R04; small new onboarding risk | Approved | 2026-09-25 | Protects the critical path and hard go-live deadline; cost is within the R01 contingency allocation ($39,000). | Yes — cost baseline +$23,800 (contingency drawdown); schedule re-baselined as Baseline 1 from 28 Sep | Change log, cost baseline, ProjectLibre schedule, risk register (R01), Trello [4.2]/[4.3], status report
CR-03 | 2026-09-10 | Privacy Officer | Make multi-factor authentication (MFA) mandatory for all students, not only staff. | 3.1, 6.1 | R03, R11, ISS-05 | Small: MFA enrolment flow + help content | +2 days in Sprint 2 (absorbed by float) | +$4,200 | Reduces R03; slightly raises R11 (MFA help tickets) | Approved | 2026-09-16 | Compliance with APP 11 'reasonable steps'; low cost; uses float not critical path. | Yes — scope statement and Sprint 2 backlog | Scope statement, Trello Sprint 2 cards, training plan (6.1), risk register

## Issue_Log
Issue log
UniConnect — Student Portal Consolidation ¦ Status date 25/09/2026 ¦ Source: data/project.yaml ¦ Maintained by: Aman Maharjan
Issue | Date | Description | Linked risk | WBS | Impact | Owner | Corrective action | Due | Status | Days open
ISS-01 | 2026-09-22 | Trial migration 1 found 4.7% duplicate student records (≈ 1,130 of 24,000). | R01 | 4.2 | Critical task 4.2 behind plan; forecast go-live slips about 10 working days without action. | Data Engineer | CR-02 cleansing mini-sprint + contractor; Registrar decides merge rules within 2 days. | 2026-10-16 | Open — in progress | 3
ISS-02 | 2026-09-15 | LMS vendor SSO token-refresh defect breaks session after 60 minutes. | R02 | 3.5 | 3.5 at 60% vs 100% planned; uses part of its 20 days float. | Solution Architect | Vendor patch escalated via CIO (C07); workaround: shorter token lifetime. | 2026-10-02 | Open | 10
ISS-03 | 2026-08-26 | Faculty of Business requested push notifications mid-sprint. | R06 | 3.2 | Potential scope creep | Project Manager | Raised CR-01; CCB deferred to Phase 2. | 2026-09-02 | Closed
ISS-04 | 2026-09-11 | Sprint 1 accessibility scan: 2 critical colour-contrast failures. | R08 | 3.1 | WCAG metric Q04 amber | UX Designer | Fix in Sprint 2 via design-system tokens; re-scan. | 2026-10-02 | In progress | 14
ISS-05 | 2026-09-08 | Privacy Officer requires MFA for all students after PIA review. | R03 | 2.4 | Scope change | Privacy Officer | Raised CR-03; approved by CCB. | 2026-09-16 | Closed
Open issues | 3

## Traceability
Traceability matrix — one WBS ID across every tool
UniConnect — Student Portal Consolidation ¦ Status date 25/09/2026 ¦ Source: data/project.yaml ¦ Maintained by: Sabikunnhar
WBS | Work package | ProjectLibre ID | Trello card | Trello link | Baseline cost | Linked risks | RACI accountable | Quality metric | Critical path
1.1 | Initiation & charter | 1 | [1.1] Initiation & charter | https://trello.com/c/w6wkNBpd | 13400 | — | Sponsor | — | Yes
1.2 | Planning & baselines | 3 | [1.2] Planning & baselines | https://trello.com/c/Ftqc11da | 12960 | — | Project Manager | — | No
1.3 | Monitoring, control & CCB | 4 | [1.3] Monitoring, control & CCB | https://trello.com/c/swANm99l | 92460 | — | Project Manager | — | No
1.4 | Closure | 5 | [1.4] Closure | https://trello.com/c/JL0qAVPk | 6700 | — | Project Manager | — | Yes
2.1 | Current-state portal audit | 7 | [2.1] Current-state portal audit | https://trello.com/c/gKHXQBHA | 14800 | — | Business Analyst | — | Yes
2.2 | Requirements workshops | 8 | [2.2] Requirements workshops | https://trello.com/c/1vNe1AZp | 15600 | R06 | Business Analyst | — | Yes
2.3 | Solution & SSO architecture | 9 | [2.3] Solution & SSO architecture | https://trello.com/c/AuYqG8s9 | 18600 | R02, R12 | Solution Architect | — | Yes
2.4 | Privacy Impact Assessment | 10 | [2.4] Privacy Impact Assessment | https://trello.com/c/pjgrHDND | 10200 | R03 | Privacy Officer | — | No
2.5 | UX & accessibility prototype | 11 | [2.5] UX & accessibility prototype | https://trello.com/c/2hhm9pSY | 17700 | R08 | UX Designer | — | No
3.1 | Sprint 1 SSO & dashboard | 13 | [3.1] Sprint 1 SSO & dashboard | https://trello.com/c/sG9i1E50 | 29300 | R02, R05, R12 | Development Lead | — | No
3.2 | Sprint 2 Enrolment & timetable | 14 | [3.2] Sprint 2 Enrolment & timetable | https://trello.com/c/Oys71NKi | 29300 | R05, R06 | Development Lead | — | No
3.3 | Sprint 3 Fees & payments | 15 | [3.3] Sprint 3 Fees & payments | https://trello.com/c/krHnWWTM | 29300 | R05, R06 | Development Lead | — | No
3.4 | Sprint 4 Services & helpdesk | 16 | [3.4] Sprint 4 Services & helpdesk | https://trello.com/c/fhyGOG3V | 29300 | R05, R06 | Development Lead | — | No
3.5 | Integration APIs (SIS, LMS, Finance) | 17 | [3.5] Integration APIs (SIS, LMS, Finance) | https://trello.com/c/k2OzKmNi | 28000 | R02 | Solution Architect | — | No
3.6 | Content & notifications configuration | 18 | [3.6] Content & notifications configuration | https://trello.com/c/QfSYD0i1 | 5600 | — | Development Lead | — | No
4.1 | Data mapping & cleansing | 20 | [4.1] Data mapping & cleansing | https://trello.com/c/4bcpHzbS | 12600 | R01 | Data Engineer | — | Yes
4.2 | Migration scripts & trial migration 1 | 21 | [4.2] Migration scripts & trial migration 1 | https://trello.com/c/ab8HgR9E | 18300 | R01, R03 | Data Engineer | — | Yes
4.3 | Trial migration 2 & reconciliation | 22 | [4.3] Trial migration 2 & reconciliation | https://trello.com/c/yqJes5HD | 36600 | R01, R03 | Data Engineer | Q01 | Yes
4.4 | Final migration | 24 | [4.4] Final migration | https://trello.com/c/MziySy58 | 8900 | R03, R04 | Data Engineer | — | Yes
5.1 | System integration testing | 25 | [5.1] System integration testing | https://trello.com/c/lwu7yxdn | 34200 | — | Test Lead | — | Yes
5.2 | Security/penetration testing | 26 | [5.2] Security/penetration testing | https://trello.com/c/BEGJQGdw | 42000 | — | Test Lead | — | No
5.3 | WCAG 2.1 AA audit | 27 | [5.3] WCAG 2.1 AA audit | https://trello.com/c/nuDiYazQ | 11000 | R08 | UX Designer | Q04 | No
5.4 | Load testing (enrolment peak) | 28 | [5.4] Load testing (enrolment peak) | https://trello.com/c/QEF3XnUk | 9800 | R07 | Solution Architect | Q03 | No
5.5 | User acceptance testing | 29 | [5.5] User acceptance testing | https://trello.com/c/0OQxOzfu | 27000 | — | Test Lead | Q05 | Yes
5.6 | Regression & defect remediation | 30 | [5.6] Regression & defect remediation | https://trello.com/c/afOrVUBH | 16160 | — | Test Lead | Q06 | No
6.1 | Training & change comms | 32 | [6.1] Training & change comms | https://trello.com/c/yEbNDknS | 22400 | R09, R11 | Project Manager | — | No
6.2 | Faculty pilot | 33 | [6.2] Faculty pilot | https://trello.com/c/6RXkUi0R | 15800 | R09, R13 | Project Manager | — | Yes
6.3 | Go-live cutover | 34 | [6.3] Go-live cutover | https://trello.com/c/DK4Gh3k2 | 234600 | R04, R07, R10 | Project Manager | — | Yes
6.4 | Hypercare | 36 | [6.4] Hypercare | https://trello.com/c/8S47PE06 | 47600 | R11 | Project Manager | Q02, Q07 | Yes
6.5 | Legacy portal decommissioning | 37 | [6.5] Legacy portal decommissioning | https://trello.com/c/66UQ2c1G | 10000 | — | Project Manager | — | Yes
| Work packages traced | 30

## Closure
Closure checklist, benefits realisation and lessons learned
UniConnect — Student Portal Consolidation ¦ Status date 25/09/2026 ¦ Source: data/project.yaml ¦ Maintained by: Aman Maharjan
# | Closure item | Owner | Status
1 | All deliverables accepted against acceptance criteria | Project Manager | Not started
2 | Registrar sign-off on final migration reconciliation | Academic Registrar | Not started
3 | UAT, security and WCAG reports archived | Test Lead | Not started
4 | Legacy portals decommissioned and data archived per retention schedule | Solution Architect | Not started
5 | Privacy Officer confirms non-production data destroyed | Privacy Officer | Not started
6 | Vendor contracts closed; contractor access revoked | Finance Office | Not started
7 | Final cost reconciliation vs budget; unused reserves returned | Project Manager | Not started
8 | Handover to BAU support (runbooks, knowledge base, SLAs) | Development Lead | Not started
9 | Benefits realisation plan handed to sponsor | Sponsor | Not started
10 | Lessons learned workshop held and register published | Project Manager | In progress (captured each sprint)
11 | Trello board archived; ProjectLibre final actuals saved | Project Manager | Not started
12 | Team released and recognised | Project Manager | Not started
13 | Closure report approved by steering committee (M7) | Sponsor | Not started
| Items complete |  | 0 of 13
Benefits realisation plan
# | Benefit / KPI | Baseline → Target | Measure date / Owner
1 | Fewer helpdesk tickets — KPI: Portal-related tickets per month | 4,200 → ≤ 2,940 (−30%) | 30/04/2027 · IT Service Desk Manager
2 | Single login — KPI: % of students using SSO + MFA | 0% → ≥ 95% | 31/03/2027 · CIO
3 | Legacy cost savings — KPI: Annual licence + support cost of legacy portals | $140k/yr → $0 after decommissioning | 30/06/2027 · Finance Office
4 | Data quality — KPI: Duplicate student records | 4.7% (trial 1) → < 0.5% | 31/03/2027 · Academic Registrar
5 | Student experience — KPI: Portal satisfaction (survey, 1–5) | 2.9 → ≥ 4.0 | 31/05/2027 · DVC (Education)
Lessons learned (what happened / impact / recommendation)
ID | What happened | Impact | Recommendation
L1 | Data profiling in 2.1 sampled only 5% of records. | Duplicates found late (ISS-01), on the critical path. | Profile 100% of keys before mapping; make data quality a gate at M2.
L2 | LMS SSO proof of concept ran inside Sprint 1. | Token defect (ISS-02) surfaced early enough to use float. | Keep technical spikes before dependent sprints.
L3 | Faculty feature requests arrived informally. | Risk of scope creep (CR-01). | Publish the CCB process in the charter and at every faculty briefing.
L4 | Accessibility scans ran from Sprint 1. | Contrast failures fixed cheaply (ISS-04). | Automate WCAG scans in the build pipeline.
L5 | EVM reported weekly from week 4. | SPI drop visible within a week of ISS-01. | Keep weekly EVM with RAG thresholds agreed by the sponsor.
L6 | Contingency reserve was sized from risk EMVs. | CR-02 was funded without new approval. | Link each reserve dollar to a named risk.
L7 | Privacy Officer joined the CCB. | MFA decision (CR-03) made in one week. | Include compliance roles on the CCB from initiation.

## Schedule_WBS
Schedule & WBS work packages (mirrors A2_GroupXX_ProjectLibre.pod)
UniConnect — Student Portal Consolidation ¦ Status date 25/09/2026 ¦ Source: data/project.yaml ¦ Maintained by: Aman Maharjan
WBS | Branch | Task | Duration (d) | PL ID | Baseline start | Baseline finish | Forecast finish | Total float (d) | Forecast float (d) | Critical | Labour cost | Fixed cost | Baseline cost (BAC) | Planned % at status | % complete | PV | EV | AC (actual) | Owner (RACI A)
1.1 | 1 | Initiation & charter | 10 | 1 | 2026-07-06 | 2026-07-17 | 2026-07-17 | 0 | 0 | Yes | 13400 | 0 | 13400 | 100% | 100% | 13400 | 13400 | 13400 | Sponsor
M1 | 1 | Charter approved | 0 | 2 | 2026-07-20 | 2026-07-17 | 2026-07-17 | 0 | 0 | Yes | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | Project Manager
1.2 | 1 | Planning & baselines | 8 | 3 | 2026-07-20 | 2026-07-29 | 2026-07-29 | 2 | 2 | No | 12960 | 0 | 12960 | 100% | 100% | 12960 | 12960 | 12960 | Project Manager
1.3 | 1 | Monitoring, control & CCB | 138 | 4 | 2026-07-30 | 2027-02-19 | 2027-02-19 | 9 | 19 | No | 92460 | 0 | 92460 | 30.43% | 30.43% | 28140 | 28140 | 28140 | Project Manager
1.4 | 1 | Closure | 5 | 5 | 2027-03-05 | 2027-03-11 | 2027-03-25 | 0 | 0 | Yes | 6700 | 0 | 6700 | 0% | 0% | 0 | 0 | 0 | Project Manager
M7 | 1 | Project closed | 0 | 6 | 2027-03-12 | 2027-03-11 | 2027-03-25 | 0 | 0 | Yes | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | Project Manager
2.1 | 2 | Current-state portal audit | 10 | 7 | 2026-07-20 | 2026-07-31 | 2026-07-31 | 0 | 0 | Yes | 14800 | 0 | 14800 | 100% | 100% | 14800 | 14800 | 14800 | Business Analyst
2.2 | 2 | Requirements workshops | 10 | 8 | 2026-08-03 | 2026-08-14 | 2026-08-14 | 0 | 0 | Yes | 15600 | 0 | 15600 | 100% | 100% | 15600 | 15600 | 15600 | Business Analyst
2.3 | 2 | Solution & SSO architecture | 10 | 9 | 2026-08-17 | 2026-08-28 | 2026-08-28 | 0 | 0 | Yes | 18600 | 0 | 18600 | 100% | 100% | 18600 | 18600 | 22320 | Solution Architect
2.4 | 2 | Privacy Impact Assessment | 10 | 10 | 2026-08-24 | 2026-09-04 | 2026-09-04 | 10 | 20 | No | 10200 | 0 | 10200 | 100% | 100% | 10200 | 10200 | 10200 | Privacy Officer
2.5 | 2 | UX & accessibility prototype | 15 | 11 | 2026-08-17 | 2026-09-04 | 2026-09-04 | 10 | 20 | No | 17700 | 0 | 17700 | 100% | 100% | 17700 | 17700 | 17700 | UX Designer
M2 | 2 | Design sign-off | 0 | 12 | 2026-09-07 | 2026-09-04 | 2026-09-04 | 10 | 20 | No | 0 | 0 | 0 | 100% | 100% | 0 | 0 | 0 | Project Manager
3.1 | 3 | Sprint 1 SSO & dashboard | 10 | 13 | 2026-08-31 | 2026-09-11 | 2026-09-11 | 5 | 15 | No | 29300 | 0 | 29300 | 100% | 100% | 29300 | 29300 | 29300 | Development Lead
3.2 | 3 | Sprint 2 Enrolment & timetable | 10 | 14 | 2026-09-14 | 2026-09-25 | 2026-09-25 | 5 | 15 | No | 29300 | 0 | 29300 | 100% | 80% | 29300 | 23440 | 23440 | Development Lead
3.3 | 3 | Sprint 3 Fees & payments | 10 | 15 | 2026-09-28 | 2026-10-12 | 2026-10-12 | 5 | 15 | No | 29300 | 0 | 29300 | 0% | 0% | 0 | 0 | 0 | Development Lead
3.4 | 3 | Sprint 4 Services & helpdesk | 10 | 16 | 2026-10-13 | 2026-10-26 | 2026-10-26 | 5 | 15 | No | 29300 | 0 | 29300 | 0% | 0% | 0 | 0 | 0 | Development Lead
3.5 | 3 | Integration APIs (SIS, LMS, Finance) | 20 | 17 | 2026-08-31 | 2026-09-25 | 2026-09-25 | 5 | 15 | No | 28000 | 0 | 28000 | 100% | 70% | 28000 | 19600 | 19600 | Solution Architect
3.6 | 3 | Content & notifications configuration | 10 | 18 | 2026-09-28 | 2026-10-12 | 2026-10-12 | 15 | 25 | No | 5600 | 0 | 5600 | 0% | 0% | 0 | 0 | 0 | Development Lead
M3 | 3 | Build complete | 0 | 19 | 2026-10-27 | 2026-10-26 | 2026-10-26 | 5 | 15 | No | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | Project Manager
4.1 | 4 | Data mapping & cleansing | 10 | 20 | 2026-08-31 | 2026-09-11 | 2026-09-11 | 0 | 0 | Yes | 12600 | 0 | 12600 | 100% | 100% | 12600 | 12600 | 15120 | Data Engineer
4.2 | 4 | Migration scripts & trial migration 1 | 15 | 21 | 2026-09-14 | 2026-10-02 | 2026-10-19 | 0 | 0 | Yes | 18300 | 0 | 18300 | 66.67% | 30% | 12200 | 5490 | 9150 | Data Engineer
4.3 | 4 | Trial migration 2 & reconciliation | 20 | 22 | 2026-10-06 | 2026-11-02 | 2026-11-16 | 0 | 0 | Yes | 36600 | 0 | 36600 | 0% | 0% | 0 | 0 | 0 | Data Engineer
M4 | 4 | Trial migration passed | 0 | 23 | 2026-11-03 | 2026-11-02 | 2026-11-16 | 0 | 0 | Yes | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | Project Manager
4.4 | 4 | Final migration | 5 | 24 | 2027-01-07 | 2027-01-13 | 2027-01-28 | 0 | 0 | Yes | 8900 | 0 | 8900 | 0% | 0% | 0 | 0 | 0 | Data Engineer
5.1 | 5 | System integration testing | 15 | 25 | 2026-11-03 | 2026-11-23 | 2026-12-07 | 0 | 0 | Yes | 34200 | 0 | 34200 | 0% | 0% | 0 | 0 | 0 | Test Lead
5.2 | 5 | Security/penetration testing | 10 | 26 | 2026-10-27 | 2026-11-09 | 2026-11-09 | 25 | 35 | No | 17000 | 25000 | 42000 | 0% | 0% | 0 | 0 | 0 | Test Lead
5.3 | 5 | WCAG 2.1 AA audit | 10 | 27 | 2026-10-20 | 2026-11-02 | 2026-11-02 | 30 | 40 | No | 11000 | 0 | 11000 | 0% | 0% | 0 | 0 | 0 | UX Designer
5.4 | 5 | Load testing (enrolment peak) | 10 | 28 | 2026-11-10 | 2026-11-23 | 2026-12-07 | 15 | 15 | No | 9800 | 0 | 9800 | 0% | 0% | 0 | 0 | 0 | Solution Architect
5.5 | 5 | User acceptance testing | 15 | 29 | 2026-11-24 | 2026-12-14 | 2027-01-06 | 0 | 0 | Yes | 27000 | 0 | 27000 | 0% | 0% | 0 | 0 | 0 | Test Lead
5.6 | 5 | Regression & defect remediation | 8 | 30 | 2026-12-01 | 2026-12-10 | 2027-01-04 | 2 | 2 | No | 16160 | 0 | 16160 | 0% | 0% | 0 | 0 | 0 | Test Lead
M5 | 5 | UAT sign-off | 0 | 31 | 2026-12-15 | 2026-12-14 | 2027-01-06 | 0 | 0 | Yes | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | Project Manager
6.1 | 6 | Training & change comms | 20 | 32 | 2026-10-27 | 2026-11-23 | 2026-11-23 | 30 | 40 | No | 14400 | 8000 | 22400 | 0% | 0% | 0 | 0 | 0 | Project Manager
6.2 | 6 | Faculty pilot | 10 | 33 | 2026-12-15 | 2027-01-06 | 2027-01-20 | 0 | 0 | Yes | 15800 | 0 | 15800 | 0% | 0% | 0 | 0 | 0 | Project Manager
6.3 | 6 | Go-live cutover | 5 | 34 | 2027-01-14 | 2027-01-20 | 2027-02-04 | 0 | 0 | Yes | 18600 | 216000 | 234600 | 0% | 0% | 0 | 0 | 0 | Project Manager
M6 | 6 | Go-live | 0 | 35 | 2027-01-21 | 2027-01-20 | 2027-02-04 | 0 | 0 | Yes | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | Project Manager
6.4 | 6 | Hypercare | 20 | 36 | 2027-01-21 | 2027-02-18 | 2027-03-04 | 0 | 0 | Yes | 47600 | 0 | 47600 | 0% | 0% | 0 | 0 | 0 | Project Manager
6.5 | 6 | Legacy portal decommissioning | 10 | 37 | 2027-02-19 | 2027-03-04 | 2027-03-18 | 0 | 0 | Yes | 10000 | 0 | 10000 | 0% | 0% | 0 | 0 | 0 | Project Manager
|  | Totals (BAC / PV / EV / AC) | [8 empty] | 651180 | 249000 | 900180 |  |  | 242800 | 221830 | 231730
Amber rows = behind plan at the status date (% complete < planned %). PV/EV/AC equal ProjectLibre BCWS/BCWP/ACWP per task.

## Assignments
Resource assignments (from the ProjectLibre plan)
UniConnect — Student Portal Consolidation ¦ Status date 25/09/2026 ¦ Source: data/project.yaml ¦ Maintained by: Aman Maharjan
WBS | Role | Units | Baseline duration (d) | Hours | Rate | Labour cost
1.1 | Project Manager | 100% | 10 | 80 | 120 | 9600
1.1 | Business Analyst | 50% | 10 | 40 | 95 | 3800
1.2 | Project Manager | 100% | 8 | 64 | 120 | 7680
1.2 | Business Analyst | 50% | 8 | 32 | 95 | 3040
1.2 | Solution Architect | 25% | 8 | 16 | 140 | 2240
1.3 | Project Manager | 50% | 138 | 552 | 120 | 66240
1.3 | Business Analyst | 25% | 138 | 276 | 95 | 26220
1.4 | Project Manager | 100% | 5 | 40 | 120 | 4800
1.4 | Business Analyst | 50% | 5 | 20 | 95 | 1900
2.1 | Business Analyst | 100% | 10 | 80 | 95 | 7600
2.1 | Data Engineer | 50% | 10 | 40 | 110 | 4400
2.1 | Solution Architect | 25% | 10 | 20 | 140 | 2800
2.2 | Business Analyst | 100% | 10 | 80 | 95 | 7600
2.2 | UX Designer | 50% | 10 | 40 | 95 | 3800
2.2 | Project Manager | 25% | 10 | 20 | 120 | 2400
2.2 | Change & Training Lead | 25% | 10 | 20 | 90 | 1800
2.3 | Solution Architect | 100% | 10 | 80 | 140 | 11200
2.3 | Security Consultant | 25% | 10 | 20 | 160 | 3200
2.3 | Developer | 50% | 10 | 40 | 105 | 4200
2.4 | Business Analyst | 50% | 10 | 40 | 95 | 3800
2.4 | Security Consultant | 50% | 10 | 40 | 160 | 6400
2.5 | UX Designer | 100% | 15 | 120 | 95 | 11400
2.5 | Developer | 50% | 15 | 60 | 105 | 6300
3.1 | Developer | 200% | 10 | 160 | 105 | 16800
3.1 | Tester | 100% | 10 | 80 | 85 | 6800
3.1 | UX Designer | 50% | 10 | 40 | 95 | 3800
3.1 | Business Analyst | 25% | 10 | 20 | 95 | 1900
3.2 | Developer | 200% | 10 | 160 | 105 | 16800
3.2 | Tester | 100% | 10 | 80 | 85 | 6800
3.2 | UX Designer | 50% | 10 | 40 | 95 | 3800
3.2 | Business Analyst | 25% | 10 | 20 | 95 | 1900
3.3 | Developer | 200% | 10 | 160 | 105 | 16800
3.3 | Tester | 100% | 10 | 80 | 85 | 6800
3.3 | UX Designer | 50% | 10 | 40 | 95 | 3800
3.3 | Business Analyst | 25% | 10 | 20 | 95 | 1900
3.4 | Developer | 200% | 10 | 160 | 105 | 16800
3.4 | Tester | 100% | 10 | 80 | 85 | 6800
3.4 | UX Designer | 50% | 10 | 40 | 95 | 3800
3.4 | Business Analyst | 25% | 10 | 20 | 95 | 1900
3.5 | Developer | 100% | 20 | 160 | 105 | 16800
3.5 | Solution Architect | 50% | 20 | 80 | 140 | 11200
3.6 | Business Analyst | 50% | 10 | 40 | 95 | 3800
3.6 | Change & Training Lead | 25% | 10 | 20 | 90 | 1800
4.1 | Data Engineer | 100% | 10 | 80 | 110 | 8800
4.1 | Business Analyst | 50% | 10 | 40 | 95 | 3800
4.2 | Data Engineer | 100% | 15 | 120 | 110 | 13200
4.2 | Tester | 50% | 15 | 60 | 85 | 5100
4.3 | Data Engineer | 100% | 20 | 160 | 110 | 17600
4.3 | Tester | 50% | 20 | 80 | 85 | 6800
4.3 | Business Analyst | 25% | 20 | 40 | 95 | 3800
4.3 | Developer | 50% | 20 | 80 | 105 | 8400
4.4 | Data Engineer | 100% | 5 | 40 | 110 | 4400
4.4 | Solution Architect | 50% | 5 | 20 | 140 | 2800
4.4 | Tester | 50% | 5 | 20 | 85 | 1700
5.1 | Tester | 150% | 15 | 180 | 85 | 15300
5.1 | Developer | 150% | 15 | 180 | 105 | 18900
5.2 | Security Consultant | 100% | 10 | 80 | 160 | 12800
5.2 | Developer | 50% | 10 | 40 | 105 | 4200
5.3 | UX Designer | 100% | 10 | 80 | 95 | 7600
5.3 | Tester | 50% | 10 | 40 | 85 | 3400
5.4 | Solution Architect | 50% | 10 | 40 | 140 | 5600
5.4 | Developer | 50% | 10 | 40 | 105 | 4200
5.5 | Tester | 100% | 15 | 120 | 85 | 10200
5.5 | Business Analyst | 100% | 15 | 120 | 95 | 11400
5.5 | Change & Training Lead | 50% | 15 | 60 | 90 | 5400
5.6 | Developer | 200% | 8 | 128 | 105 | 13440
5.6 | Tester | 50% | 8 | 32 | 85 | 2720
6.1 | Change & Training Lead | 100% | 20 | 160 | 90 | 14400
6.2 | Change & Training Lead | 50% | 10 | 40 | 90 | 3600
6.2 | Business Analyst | 50% | 10 | 40 | 95 | 3800
6.2 | Developer | 100% | 10 | 80 | 105 | 8400
6.3 | Solution Architect | 100% | 5 | 40 | 140 | 5600
6.3 | Developer | 200% | 5 | 80 | 105 | 8400
6.3 | Data Engineer | 50% | 5 | 20 | 110 | 2200
6.3 | Project Manager | 50% | 5 | 20 | 120 | 2400
6.4 | Developer | 200% | 20 | 320 | 105 | 33600
6.4 | Change & Training Lead | 50% | 20 | 80 | 90 | 7200
6.4 | Tester | 50% | 20 | 80 | 85 | 6800
6.5 | Solution Architect | 50% | 10 | 40 | 140 | 5600
6.5 | Data Engineer | 50% | 10 | 40 | 110 | 4400

## Resources
Resources and rates (AUD)
UniConnect — Student Portal Consolidation ¦ Status date 25/09/2026 ¦ Source: data/project.yaml ¦ Maintained by: Aman Maharjan
Role | Count (FTE) | Rate per hour | Type | Baseline hours | Baseline labour cost
Project Manager | 1 | 120 | Work | 776 | 93120
Business Analyst | 1 | 95 | Work | 928 | 88160
Solution Architect | 1 | 140 | Work | 336 | 47040
Developer | 3 | 105 | Work | 1848 | 194040
Data Engineer | 1 | 110 | Work | 500 | 55000
Tester | 2 | 85 | Work | 932 | 79220
UX Designer | 1 | 95 | Work | 400 | 38000
Change & Training Lead | 1 | 90 | Work | 380 | 34200
Security Consultant | 1 | 160 | Work (contract) | 140 | 22400
Total |  |  |  | 6240 | 651180

## Lookups
Lookups & scoring scales
UniConnect — Student Portal Consolidation ¦ Status date 25/09/2026 ¦ Source: data/project.yaml ¦ Maintained by: Sabikunnhar
Likelihood | Label | Band | Probability |  | Strategy | Status | CCB decision | RAG | RACI | Holidays (NSW + SCU shutdown)
1 | Rare | < 10% | 5% |  | Avoid | Open | Approved | Green | R | 2026-10-05 | Labour Day (NSW)
2 | Unlikely | 10–30% | 15% |  | Mitigate | In progress | Deferred | Amber | A | 2026-12-24 | University shutdown
3 | Possible | 30–50% | 40% |  | Transfer | Closed | Rejected | Red | C | 2026-12-25 | Christmas Day
4 | Likely | 50–80% | 65% |  | Accept | Not started | Pending | Grey | I | 2026-12-28 | Boxing Day (observed)
5 | Almost certain | > 80% | 90% |  | Exploit | Done |  |  |  | 2026-12-29 | University shutdown
[5 empty] | Enhance |  |  |  |  | 2026-12-30 | University shutdown
Impact | Label | Cost | Schedule | Other | Share |  |  |  |  | 2026-12-31 | University shutdown
1 | Insignificant | < $5k | < 2 days | No external visibility | [5 empty] | 2027-01-01 | New Year's Day
2 | Minor | $5k–15k | 2–5 days | Internal complaints | [5 empty] | 2027-01-26 | Australia Day
3 | Moderate | $15k–40k | 1–2 weeks | Student complaints; SRC attention | [5 empty] | 2027-03-26 | Good Friday
4 | Major | $40k–100k | 2–4 weeks; milestone missed | Media/regulator enquiry | [5 empty] | 2027-03-29 | Easter Monday
5 | Severe | > $100k | > 4 weeks; go-live deadline missed | Notifiable data breach; TEQSA action
Rating | Min score | Max score | Colour
Low | 1 | 4 | green
Medium | 5 | 9 | yellow
High | 10 | 16 | orange
Extreme | 20 | 25 | red